## Sheet1
Assumptions:
1) Living Room is on the bottom floor
2) Home is located 5 miles from contractor site,
therefore no additional expense is allocated for travel to site
3) All require equipment; truck & misc. supplies is owned and paid for
4) Materials priced separately, so that home owner can directly purchase if they want to.
If contractor purchases maters, delivery fee is part of overhead
5) Industry standard overhead rate is 10% of labor cost
(Project Management is included in Overhead rate)
6) Industry standard profit is 10% after overhead
7) One day laborer at $150/day. Job will be completed in one eight hour day.
Living Room Exercise |  | (Labor Costs)
Room Dimensions |  | 16'x12' (one door)
Demolition
| Remove Existing Floor Covering |  | 150
| Remove Existing Base Moulding |  | 75
| Nail Strips to be removed |  | 50
| Total Demolition |  | 275
New Construction
| Prepare Existing Slab |  | 150
| Wood Frame & Subfloor Installation |  | 350
| Finish Flooring Boards & Trim Installation |  | 250
| Total Construction |  | 750
| Total Labor |  | 1025
| 10% Overhead |  | 102.5
| 10% Profit |  | 112.75
| Total Contract |  | 1240.25
Note:
Estimates provided by Michael Zimmermann (contact information attached)
Cost estimating methodology uses Analogous techniques for similar size
and for similar size and scope
Living Room Exercise |  | (Material Costs)
Room Dimensions |  | 16'x12' (one door)
sub floor
total area for floor, 8X12=96 sq ft
2x2 lumber (rough exposed) 8' lengths $8.35ea
|  | 6 boards=10sq ft, 60boards@8.35= |  | 501
wood floor
| carton is 22sq ft@219.78/carton, 5cartons= |  |  | 1098.9
base boards
12x16 (calculated for complete room-doorway)= 52'
| russet base $7.56/8' board 8x$7.56/8' board = |  |  | 756
| Total Materials |  |  | 2355.9
Subfloor made of 2x2 lumber |  |  | wood floor |  | base boards