## RiskReg
Risk Checklist
Project Number | Team # 3
Date | 2008-08-26
Project Title | National Railway System
Project Manager | Raisa Spector
Risk Number | Risk Category | Risk Name | Probability | Impact | Risk Score | Risk Cause | Response Plan Y/N | Responsible Party
33 | External-Damage | Fraud, embezzlement | 7 | 8 | 56 | financial
20 | External- Theft | Equipment or material have been stolen | 7 | 6 | 42 | local people going through hard economic times
21 | External-Damage | Major unexpected damage to Equipment | 7 | 6 | 42 | poor maintenance of equipment
31 | Project Management-Scope | Requirements change | 6 | 7 | 42 | requirements creep
29 | Project Management-Scheduling | Failure to meet project schedule | 6 | 6 | 36 | schedule delay
38 | Technical- Requirements | Faulty electric system | 4 | 8 | 32 | electrical
10 | Organizational-Resources | Kidnapping of staff | 5 | 6 | 30 | increasing number of kidnappings in the corporate world
16 | External- Weather | Early start of the rainy season | 5 | 6 | 30 | bad judgment by weather forecasters
17 | External- Weather | Rain season extends | 5 | 6 | 30 | bad judgment by weather forecasters
23 | External-Subcontractors and Suppliers | Equipment not ready | 5 | 6 | 30 | schedule delay
27 | Project Management-Planning | Scope statement does not detail all requirements | 5 | 6 | 30 | unsatisfied requirements
35 | External-Funding | Not able to acquire adequate funding in time for the project | 5 | 6 | 30 | financial
3 | External-Regulatory | Government instability (ex: Revolution) | 4 | 7 | 28 | loss of public support for government
36 | Organizational-Resources | Difficulties in recruiting skilled workers | 4 | 7 | 28 | manpower/training
39 | Project Management-Planning | Surveying task may not provide reliable mapping | 4 | 7 | 28 | survey inaccurate
41 | Technical-Quality | Government Committee does not accept a job | 3 | 9 | 27 | poor quality of the embankment
4 | External-Regulatory | Financiers/Bank refuses to lend scheduled money | 5 | 5 | 25 | our company receives bad credit rating
25 | Technical- Requirements | Unfitting equipment purchased | 4 | 6 | 24 | equipment
26 | Project Management-Controlling | Failure to secure financing | 6 | 4 | 24 | financial
34 | Project Management-Planning | Failure to identify an all stakeholders | 4 | 6 | 24 | stakeholders not identified
19 | Technical-Environment conditions | Terrain is more difficult to prepare for construction | 3 | 7 | 21 | poor surveying done
30 | Project Management-Scheduling | Contract delayed | 3 | 7 | 21 | schedule delay
2 | External-Regulatory | Devaluation of the local currency | 6 | 3 | 18 | economic inflation
40 | Technical-Performance and Reliability | Acquired equipment is old and does not perform | 3 | 6 | 18 | equipment
6 | External-Regulatory | War breaks out | 2 | 8 | 16 | tension between Venezuela and neighboring countries
18 | External- Weather | Natural Disaster (mud slides, major storm, etc). | 2 | 8 | 16 | uncontrollable Mother nature
37 | Organizational-Resources | Inability to acquire appropriate supplies such as food and water for workers | 2 | 8 | 16 | logistics
7 | External-Regulatory | Sudden tax imposition by local government | 3 | 5 | 15 | government needs quick financing
22 | Organizational-Project Dependencies | Materials do not arrive on schedule for construction | 3 | 5 | 15 | schedule delay
13 | Organizational-Resources | Employees get sick from RR tie treatment (creosote) | 2 | 7 | 14 | lack of safety guidelines and safety equipment
14 | External-Subcontractors and Suppliers | A critical sub contractor pulls out of job | 3 | 4 | 12 | subcontractor having financial difficulties
24 | Project Management-Controlling | Cost of equipment increases | 3 | 4 | 12 | price increase
1 | External-Regulatory | Collapse of Venezuela's Banking System (as happened in January 1994) | 2 | 5 | 10 | civil unrest in the country
32 | Technical-Technology | Computers unable to connect to internet | 5 | 2 | 10 | network connectivity
5 | External-Regulatory | Government regulations change for railroad project | 3 | 3 | 9 | government receives pressure from outside to change regulations
9 | Organizational- Resources | Employees strike for more wages | 2 | 3 | 6 | employees of other industries gaining wage concessions
8 | External-Customer | Squatters on RR property unite not to move | 2 | 2 | 4 | squatters require staying in current position
12 | Organizational-Resources | Communication problems due to language differences | 2 | 2 | 4 | language differences
28 | Project Management-Planning | Unable to secure liability insurance | 1 | 3 | 3 | insurance
11 | Organizational-Resources | President of company leaving country for Colombian girlfriend | 1 | 2 | 2 | wife of Colombian president not satisfying the president
15 | Organizational-Resources | Health and safety inspection are not up to standards | 2 | 1 | 2 | poor job done on health and safety issues
Surveying task may not provide reliable mapping.
Note on D46: Ricardo: Finally he got married. We are ok for a list 6 months >:-).

## Prob. & Imp.
Probability | 10
9
| 8 | [10 empty] | High Risk | 45
| 7 | [5 empty] | 20,21 |  | 33 |  |  | Medium Risk | 24
| 6 |  |  | 2 | 26 |  | 29 | 31 |  |  |  | Low Risk <= | 23
| 5 |  | 32 |  |  | 4 | 23,35,10,16,17,27 | 10
| 4 | [5 empty] | 34,25 | 39,36,3 | 38
| 3 |  |  | 5 | 14,24 | 7,22 | 40 | 19,30 |  | 41
| 2 | 15 | 12,8 | 9 |  | 1 |  | 13 | 37,6,18
| 1 |  | 11 | 28
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Impact