Controlling Project Costs and Risks

Summer 2008

Team #3 (Raisa, Omar, Roberto, David, Mark, Suzanne)

Week #2 and #3 Team Exercise

Scope Statement for Charity Project

Project and Project Objectives:

We are a company with 1000 people located in the same building in San Diego, California. In April 2008, a tragic situation developed with one of our colleagues. Brian Johnson, a member of our IT team, was diagnosed with a life-threatening liver condition and requires a kidney transplant. Miraculously, a suitable donor was found. Brian has health insurance that will cover his part of the operation, but the donor does not have health insurance. Our company has decided to help Brian and his family raise the $100,000 dollars necessary for the transplant operation to take place.

Service Requirements and characteristics:

We have decided to implement four different programs to raise money. First, we will have a capital campaign designed to solicit monetary donations. Second, we will organize a soccer tournament open to employees, along with their friends and family. Third, we will work with a food catalog company such as Charles Chips and pass out catalogs with items that can be ordered. (A percentage of catalog sales come back to us.) Lastly, we will organize a phone bank for several days and have employees make calls to solicit donations.

Product acceptance criteria:

The project is successful if and when $100,000 dollars (our four campaigns + company match) is raised for the Johnson family.

Project Boundaries:

The boundaries of this project will be limited to the project objectives and the service requirements as outlined above.  Employees unable to perform any of the duties outlined in the service requirements and characteristics section must inform the project manager immediately upon notice of inability to perform required designated tasks.

Project Requirements and Deliverables:

The project management related deliverables are: Scope management plan, WBS, cost analysis, etc.

The charity campaign deliverables are: four fundraising campaigns and $50,000 (plus company match of $50,000 for a total of $100,000).

Project constraints:

All volunteers  will be available only on a part-time basis.

Preliminary estimate cannot be specified with accuracy because of unpredictability of the donations.

Controlling Project Costs and Risks

Summer 2008

Team #3 (Raisa, Omar, Roberto, David, Mark, Suzanne)

Week #2 and #3 Team Exercise

Project assumptions:

- All 1000 employees will participate in at least one of the four fundraising campaigns.

- The Johnson Family will support us in any way they can (e.g., email messages to company, appearance at soccer tournament, etc.).

- The company will match all donations up to $50,000.

- Fundraising efforts will be on a volunteer basis and man-hour efforts required to accomplish tasks will not be funded.

Initial project organization:

The project is organized in 4 parts, it will be divided by 4 different committees responsible for all WBS elements identified in their section of responsibility.  They will report to the Project Manager and report on schedule and cost daily.

Initial defined risks:

1.  Brian dies prior to kidney transplant.

2.  Fundraising initiatives do not cover cost of medical expenses.

3. Donor backs out of donating liver.

Schedule milestones:

Project initiation: August 5, 2008

Capital campaign: August 9, 2008

Soccer tournament: August 16, 2008

Catalog fundraiser: August 23, 2008

Phone Bank: August 30, 2008

Provide Money to hospital to cover medical expenses: August 31, 2008

Initial WBS:

- Managing the projects

  - Designate a project manager for the overall project

      - Work with web team to put information on company intranet

  - Designate leaders for each of the four campaigns

  - Write a preliminary scope statement

  - Write a work breakdown structure

  - Create a cost analysis

      - Capital campaign

      - Soccer tournament

      - Catalog fundraiser

      - Phone bank

  - Execute the plan

Controlling Project Costs and Risks

Summer 2008

Team #3 (Raisa, Omar, Roberto, David, Mark, Suzanne)

Week #2 and #3 Team Exercise

  - Monitor activities

  - Write project wrap up report

- Capital campaign

  - Design an overall campaign (slogan, theme, look and feel)

  - Add information and donation form to company intranet

  - Create/Print donation envelopes

  - Create/Print banners/posters for company building

- Soccer tournament

  - Research how to organize a soccer tournament

  - Create information sheet and signup form for company intranet

  - Reserve fields

  - Have t-shirts printed

  - Get equipment (soccer balls, goals, etc.)

  - Recruit volunteers to work on day of tournament

- Catalog fundraiser

  - Research different catalog fundraisers

  - Recruit volunteers to process order forms and pass out merchandise

  - Select a company and contact them

  - Place products in catalog

  - Work with web team to put information on company intranet

  - Work with corporate mailroom to distribute catalogs

  - Collect order forms and process

  - Work with company to resolve discrepancies

  - Receive and sort orders

  - Use volunteers to pass out merchandise along with a thank you card

- Phone bank

  - Research how to organize and implement a phone bank

  - Find a suitable location and equipment within the company to hold phone bank campaign

  - Work with web team to put information on company intranet

  - Recruit callers

  - Hold a training session for callers

      - With callers, develop a script to use for phone calls

      - Discuss phone etiquette and tips

  - Hold phone bank campaign

Order of magnitude cost estimate:

Because this project does not have initial funding, we do not have to specify order of magnitude cost estimate.

Project CM requirements:

Document changes will be handled by CM lead.  All revisions that feed into master documents will need approval by the CM lead.  Document version control will be in use and back up systems will be in place to ensure document quality control.

Money obtained through the fundraising events will be the responsibility of the finance department.