## Cost Estimate
|  |  | Internal Labor Rate ($/hr) | 30
|  |  | Materials/Tools Overhead | 0.08
|  |  | Labor Overhead Rate | 0.12
[6 empty] | Internal |  | External |  |  | Int & Ext
|  |  | Total Costs |  |  | 4771.2 |  | 1849.932 |  |  | 6621.132
| WBS | Work Breakdown Structure | Internal Cost |  |  |  | External Cost |  | Total Cost (Internal & External) |  |  | HRS
outline level | outline | Name | Materials | Materials (incl. OVH) | Labor (hrs) | Labor (incl. OVH) | Materials | Materials (incl. OVH) | Total Material Cost | Total Labor Cost | Total Cost | Duration (hours)
1 | 1 | Landscape |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2 | 1.1 | Project management | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3 | 1.1.1 | Initiating | 0 | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
3 | 1.1.2 | Project start | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
3 | 1.1.3 | Project charter | 0 | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
3 | 1.1.4 | Scope statement | 0 | 0 | 16 | 537.6 |  | 0 | 0 | 537.6 | 537.6 | 16
2 | 1.1.5 | WBS | 0 | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
3 | 1.1.6 | Contract with homeowner | 0 | 0 | 16 | 537.6 | 0 | 0 | 0 | 537.6 | 537.6 | 16
3 | 1.1.6.1 | Execute contract |  | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
3 | 1.1.6.2 | Receive deposit to begin work |  | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
3 | 1.2 | Design | 0 | 0 | 0.5 | 16.8 | 0 | 0 | 0 | 16.8 | 16.8 | 0.5
2 | 1.2.1 | Measurement | 0 | 0 | 3 | 100.8 |  | 0 | 0 | 100.8 | 100.8 | 3
3 | 1.2.2 | Landscape design |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
3 | 1.2.2.1 | Irrigation system design |  | 0 | 4 | 134.4 |  | 0 | 0 | 134.4 | 134.4 | 4
3 | 1.2.2.2 | Shade tree location design |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
3 | 1.2.3 | Choosing and negotiation with owner the types of materials and components |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3 | 1.2.3.1 | Choosing fill material | 0 | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.2.3.2 | Choosing type of sprinkler system, valve, controller, and sprinkler heads |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.2.3.3 | Choosing top soil material |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.3 | Removing existing landscaping |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.3.1 | Removing existing ground cover in entire front yard |  | 0 | 8 | 268.8 |  | 0 | 0 | 268.8 | 268.8 | 8
| 1.3.2 | Hauling away existing materials ($57.00 landfill fee) |  | 0 | 4 | 134.4 | 57 | 61.56 | 61.56 | 134.4 | 195.96 | 4
| 1.4 | Execution |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.1 | Import fill |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.1.1 | Buy fill material (3 inches thick) |  | 0 | 2 | 67.2 | 170 | 183.6 | 183.6 | 67.2 | 250.8 | 2
| 1.4.1.2 | Deliver fill material |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.1.3 | Spread new fill material and level all areas of the lawn |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.4.2 | Compaction |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.2.1 | Rent a roller ($15.00 per day rental fee) |  | 0 | 1 | 33.6 | 15 | 16.2 | 16.2 | 33.6 | 49.8 | 1
| 1.4.2.2 | Prepare roller with water to increase weight |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.2.3 | Roll the fill material for compacting |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.3 | Top soil (3 inches thick) |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.3.1 | Buy top soil |  | 0 | 2 | 67.2 | 390 | 421.2 | 421.2 | 67.2 | 488.4 | 2
| 1.4.3.2 | Deliver top soil |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.3.3 | Spread top soil |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.4 | Compaction |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.4.1 | Roll the top soil for compacting |  | 0 | 1 | 33.6 | 15 | 16.2 | 16.2 | 33.6 | 49.8 | 1
| 1.4.5 | Underground sprinklers and controllers |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.5.1 | Stake and line underground sprinklers and controllers |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.5.2 | Excavate for underground sprinklers and controllers |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.5.3 | Install plumb stakes to support irrigation heads and valve manifold |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.4.5.4 | Dig hole for tree |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.6 | Irrigation |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.6.1 | Purchase the heads, the risers, the connectors, control valves, piping and PVC cement |  | 0 | 3 | 100.8 | 169.9 | 183.492 | 183.492 | 100.8 | 284.292 | 3
| 1.4.6.2 | Digging trenches |  | 0 | 0.5 | 16.8 |  | 0 | 0 | 16.8 | 16.8 | 0.5
| 1.4.6.3 | Cut all piping |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.4.6.4 | Dry fit assembly |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.4.6.5 | Install wiring for control valves to timer |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.6.6 | Assemble with PVC cement |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.4.6.7 | Wait 24-hours for drying |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.6.8 | Short duration testing of all circuits |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.7 | Shade tree |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.7.1 | Purchase tree (20 foot Jacaranda tree at $299.00 = $40.00 delivery fee) |  | 0 | 1 | 33.6 | 339 | 366.12 | 366.12 | 33.6 | 399.72 | 1
| 1.4.7.2 | Tree delivered |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.7.3 | Plant tree |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.8 | Plant sod/lawn |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.4.8.1 | Purchase sod |  | 0 | 1 | 33.6 | 557 | 601.56 | 601.56 | 33.6 | 635.16 | 1
| 1.4.8.2 | Sod delivered |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.4.8.3 | Sold placed |  | 0 | 4 | 134.4 |  | 0 | 0 | 134.4 | 134.4 | 4
| 1.4.8.4 | Sod rolled |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.5 | Closeout |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 1.5.1 | Demonstrate system to homeowner |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1
| 1.5.2 | Instruction on timer usage |  | 0 | 2 | 67.2 |  | 0 | 0 | 67.2 | 67.2 | 2
| 1.5.3 | Collect balance of money |  | 0 | 1 | 33.6 |  | 0 | 0 | 33.6 | 33.6 | 1

## Assumptions_Notes
Assumptions
We are using a combination of suppliers
We are using ourselves (internal labor - 2 people) for the work - no external labor will be hired
Our initial PM costs are high - we do lots of planning up front
We, as a company, have almost all necessary equipment (trucks, tools, etc.)
Suzanne obtained estimates for different tasks/materials from 3 places
Yard is 35 feet x 40 feet for a total of 1400 square feet
Project Requirements
Remove/dispose of 1400 sq ft of existing ground cover (use our tools/truck - $57.00 landfill fee)
Import/buy fill $10 per cb yd (40 ft x 35 ft at 4 inches thick = 17 cb yds) = $170.00
Excavate for underground sprinklers and controllers
Grading (fine level)
Top soil $30 per cubic yard (40 ft x 35 ft at 3 inches thick = 13 cubic yds) = $390.00
Irrigation/sprinklers
8 heads at $2.97 each ($23.76)
Risers 16 at .49 each ($7.84)
Connectors 16 at .39 and 2 at .85 each ($6.24 + $1.70 = $7.94)
Valves 3 at $12.97 each ($38.91)
Piping $4.71 per 10 foot section - we need 120 feet of pipe ($56.52)
PVC cement $4.98 per pint - we need 2 pints ($9.96)
Controller 1 at $24.97
Total cost for all irrigation materials = $169.90
Sod $1.99 per 5 sq ft piece for 1400 sq ft yard = $557
Shade tree (1, 20-foot tall Jacaranda tree) = $299
Key Numbers
Total cost = $6621.00
Total hours = 132 (16.5 days)
Total materials/fees = $1850.00
Total labor = $4771.00
Average cost per square foot = $4.73
Average hourly rate = $36.14
Materials overhead rate = 8%
Labor overhead rate = 12%
Total square feet = 1400

## WBS
outline level | outline | Name | duration
1 | 1 | Landscape | 16.5 days
2 | 1.1 | Project management | 11 days
3 | 1.1.1 | Initiating | 1 day
3 | 1.1.2 | Project start | 0 days
3 | 1.1.3 | Project charter | 1 day
3 | 1.1.4 | Scope statement | 2 days
3 | 1.1.5 | WBS | 1 day
3 | 1.1.6 | Contract with homeowner | 2 days
4 | 1.1.6.1 | Execute contract | 1 day
4 | 1.1.6.2 | Receive deposit to begin work | 1 day
2 | 1.2 | Design | 1.38 days
3 | 1.2.1 | Measurement | 3 hours
3 | 1.2.2 | Landscape design | 0.63 days
4 | 1.2.2.1 | Irrigation system design | 4 hours
4 | 1.2.2.2 | Shade tree location design | 1 hour
2 | 1.2 |  | 0
3 | 1.2.3 | Choosing and negotiation with owner the types of materials and components | 0.38 days
4 | 1.2.3.1 | Choosing fill material | 1 hour
4 | 1.2.3.2 | Choosing type of sprinkler system, valve, controller, and sprinkler heads | 1 hour
4 | 1.2.3.3 | Choosing top soil material | 1 hour
2 | 1.3 | Removing existing landscaping | 1.5 days
3 | 1.3.1 | Removing existing ground cover in entire front yard | 1 day
3 | 1.3.2 | Hauling away existing materials | 4 hours
2 | 1.4 | Execution | 6.13 days
3 | 1.4.1 | Import fill | 0.63 days
4 | 1.4.1.1 | Buy fill material | 2 hours
4 | 1.4.1.2 | Deliver fill material | 1 hour
4 | 1.4.1.3 | Spread new fill material and level all areas of the lawn | 2 hours
3 | 1.4.2 | Compaction | 0.38 days
4 | 1.4.2.1 | Rent a roller | 1 hour
4 | 1.4.2.2 | Prepare roller with water to increase weight | 1 hour
4 | 1.4.2.3 | Roll the fill material for compacting | 1 hour
3 | 1.4.3 | Top soil | 0.5 days
4 | 1.4.3.1 | Buy top soil | 2 hours
4 | 1.4.3.2 | Deliver top soil | 1 hour
4 | 1.4.3.3 | Spread top soil | 1 hour
3 | 1.4.4 | Compaction | 0.13 days
4 | 1.4.4.1 | Roll the top soil for compacting | 1 hour
3 | 1.4.5 | Underground sprinklers and controllers | 0.63 days
4 | 1.4.5.1 | Stake and line underground sprinklers and controllers | 1 hour
4 | 1.4.5.2 | Excavate for underground sprinklers and controllers | 1 hour
4 | 1.4.5.3 | Install plumb stakes to support irrigation heads and valve manifold | 1 hours
4 | 1.4.5.4 | Dig hole for tree | 1 hour
3 | 1.4.6 | Irrigation | 2.88 days
4 | 1.4.6.1 | Purchase the heads, the risers, the connectors, control valves, piping and PVC cement | 3 hours
4 | 1.4.6.2 | Digging trenches | 0.5 days
4 | 1.4.6.3 | Cut all piping | 2 hours
4 | 1.4.6.4 | Dry fit assembly | 2 hours
4 | 1.4.6.5 | Install wiring for control valves to timer | 1 hour
4 | 1.4.6.6 | Assemble with PVC cement | 2 hours
4 | 1.4.6.7 | Wait 24-hours for drying | 1 day
4 | 1.4.6.8 | Short duration testing of all circuits | 1 hour
3 | 1.4.7 | Shade tree | 0.38 days
4 | 1.4.7.1 | Purchase tree | 1 hour
4 | 1.4.7.2 | Tree delivered | 1 hour
4 | 1.4.7.3 | Plant tree | 1 hour
3 | 1.4.8 | Plant sod/lawn | 1 day
4 | 1.4.8.1 | Purchase sod | 1 hour
4 | 1.4.8.2 | Sod delivered | 1 hour
4 | 1.4.8.3 | Sold placed | 4 hours
4 | 1.4.8.4 | Sod rolled | 2 hours
2 | 1.5 | Closeout | 0.5 days
3 | 1.5.1 | Demonstrate system to homeowner | 1 hour
3 | 1.5.2 | Instruction on timer usage | 2 hours
3 | 1.5.3 | Collect balance of money | 1 hour