## Sheet1
Risk Checklist
Project Number | Team # 3
Date | 2008-08-10
Project Title | National RailWay System
Project Manager | Raisa Spector
Risk Number | Risk Category | Risk Name | Risk Score | Response Plan Y/N | Responsible Party
1 | External-Government Lvl | Collapse of Venezuela's Banking System. As it happened in January 1994.
2 | External-Government Lvl | Devaluation of the local currency.
3 | External-Government Lvl | Government instability (ex: Revolution)
4 | External-Government Lvl | Financiers/Bank refuses to lend scheduled money
5 | External-Government Lvl | Government regulations change for railroad project
6 | External-Government Lvl | War breaks out
7 | External-Government Lvl | Sudden tax imposition by local government
8 | External-Government Lvl | Squatters on RR property unite not to move
9 | Personnel | Employees strike for more wages
10 | Presonnel - External | Kidnapping of staff.
11 | Personnel | President of the company leaving the country for a Colombian girlfriend.
12 | Personnel | Communication problems due to language differences
13 | Organizational | Employees get sick from RR tie treatment (creosote)
14 | Organizational | A critical sub contractor pulls out of job
15 | Organizational | Health and safety inspection are not up to standards
16 | External | Early start of the rainy season
17 | External | Rain season extends
18 | External | Natural Disaster (mud slides, major storm, etc).
19 | External | Terrain is more difficult to prepare for construction
20 | External | Equipment or material have been stolen
21 | External | Major unexpected damage to Equipment
22 | Organizational | Materials do not arrive on schedule for construction
23 | Technical | Equipment not ready
24 | Budget | Cost of equipment increases
25 | Organizational | Unfitting equipment purchased
26 | Budget | Failure to secure financing
27 | Project Management | Scope statement does not detail all requirements
28 | Funancial | Unable to secure liability insurance
29 | Schedule | Failure to meet project schedule
30 | Schedule | Contract delayed
31 | Scope | Requirements change
32 | Technical | Computers unable to connect to internet
33 | External | Fraud, embezzlement.
34 | Project Management | Failure to identify an all stakeholders
35 | External-Government Lvl | Not able to acquire adequate funding in time for the project
36 | Organizational | Difficulties in recruiting skilled workers
37 | Organizational | Inability to acquire appropriate supplies such as food and water for workers
38 | Organizational | Faulty electric system.
39 | Project Management | Surveying task may not provide reliable mapping.
Surveying task may not provide reliable mapping.